## 7-Day Plan
# | Day | Theme | Phase | Task | What's involved (scope of work) | Deliverable / Done when | Owner | Status | Start Date | End Date | Notes
1 | 1 | Foundation & Infrastructure | Foundation | Unify the two repositories into one app | Merge the separate Odoo and Zoho ZATCA-middleware codebases into a single Next.js 16 + TypeScript application that shares one ZATCA compliance core with pluggable accounting-software adapters. Establish the repository structure, dependency baseline and build pipeline. | zatca-middleware-dev builds green; shared core + adapter layout in place | Claude | Done |  |  | Pushed to GitHub
2 | 1 | Foundation & Infrastructure | Foundation | Design & apply the multi-tenant database | Design and apply the full PostgreSQL schema on Supabase (organizations, tenant members, ZATCA profiles, invoices, transaction logs, Odoo/Zoho configs, async jobs) with Row-Level-Security so every business can only read its own data. | 10 tables + RLS policies live; tenant data provably isolated | Claude | Done |  |  | migrations 001-003
3 | 1 | Foundation & Infrastructure | Foundation | Google authentication + sessions | Implement Sign-in with Google via Supabase Auth with cookie-based sessions and middleware route-protection, replacing the old custom email/password model. Unauthenticated users are redirected to login. | Google login works end-to-end; protected routes enforced | Claude | Done |  |  | verified live
4 | 1 | Foundation & Infrastructure | Foundation | Automatic tenant provisioning | On a user's first login, automatically create their organization and link them as a member — establishing the tenant boundary used by every query and policy in the system. | Org + membership created on first login (DB-verified) | Claude | Done |  |  | multi-tenant isolation confirmed
5 | 1 | Foundation & Infrastructure | Foundation | Encrypt secrets at rest (AES-256-GCM) | Add authenticated AES-256-GCM encryption so ERP credentials, ZATCA private keys and CSIDs are stored only as ciphertext and decrypted in memory when needed; master key held in environment config. | All sensitive credentials encrypted at rest | Claude | Done |  |  | fixes a prior cleartext gap
6 | 1 | Foundation & Infrastructure | Foundation | ZATCA environment resolver (Demo/Real) | Build the configurable resolver that maps a tenant's environment to the correct ZATCA API base URL: Demo -> simulation (OTP 123456, nothing legally filed) vs Real -> core (live filing). | Switchable endpoints; Demo vs Real cleanly separated | Claude | Done
7 | 2 | ZATCA Core & Onboarding | ZATCA Core | Consolidate the Phase-2 compliance core | Bring the proven ZATCA Phase-2 engine into the unified app: UBL 2.1 XML generation (standard + simplified, 388/381/383), SHA-256 hashing with canonicalization, ECDSA secp256k1 signing, XAdES signature block, and TLV QR encoding. | Shared compliance core compiles and runs in the unified app | Claude | Done |  |  | from the tested repos
8 | 2 | ZATCA Core & Onboarding | ZATCA Core | Wire ZATCA onboarding into the tenant flow | Connect the proven onboarding sequence — generate keypair + CSR, request the Compliance CSID, run the compliance sample-invoice checks, then issue the Production CSID — to the per-tenant journey, executed against ZATCA simulation. | A tenant completes full onboarding from the UI (OTP 123456) | Claude | Done |  |  | runs against simulation
9 | 2 | ZATCA Core & Onboarding | ZATCA Core | Fix the production-CSID issuance | Audit and correct the onboarding finalize step, which currently persists a placeholder production CSID instead of the real certificate returned by ZATCA; ensure the genuine CSID is stored and used for clearance. | Real production CSID stored and used for signing/clearance | Claude | To Do |  |  | found in end-to-end audit
10 | 2 | ZATCA Core & Onboarding | ZATCA Core | Validate crypto against the official ZATCA SDK | Validate canonicalization, the invoice hash, and the digital signature byte-for-byte against the official ZATCA Java SDK reference output for known invoices — the single highest-risk correctness item before go-live. | Hash + signature match the SDK reference exactly | Claude | To Do |  |  | correctness gate
11 | 2 | ZATCA Core & Onboarding | ZATCA Core | Demo <-> Real environment plumbing | Finish wiring so a tenant's onboarding, credentials and submissions consistently target the chosen ZATCA environment, with Demo and Real credentials stored separately and never mixed. | Per-tenant environment honoured across onboarding + clearance | Claude | In Progress
12 | 3 | Adapters & Async Pipeline | Adapters | Odoo adapter (JSON-RPC + webhook + write-back) | Integrate the Odoo adapter: JSON-RPC client, inbound webhook (pull/push), automatic provisioning of x_zatca_* fields on account.move, and write-back of UUID / QR / signed PDF / status to the invoice record. | Odoo invoice -> clearance -> write-back works on simulation | Claude | Done |  |  | ported from the Odoo repo
13 | 3 | Adapters & Async Pipeline | Adapters | Zoho Books adapter (OAuth + webhook + write-back) | Integrate the Zoho Books adapter: OAuth2 refresh-token authentication, region-aware API, inbound webhook, cf_zatca_* custom fields, and write-back via custom fields + timeline comments + file attachments. | Zoho invoice -> clearance -> write-back works on simulation | Claude | Done
14 | 3 | Adapters & Async Pipeline | Adapters | Real connection test + field provisioning | Make connecting an accounting software genuinely call the live Odoo/Zoho API to authenticate; only mark 'connected' on real success, surface the real error otherwise, and run real custom-field provisioning. No fabricated states. | Connection verified live; real ERP errors shown to the user | Claude | Done |  |  | 'no fake' requirement
15 | 3 | Adapters & Async Pipeline | Pipeline | Asynchronous job queue + worker | Build the async pipeline so clearance is reliable at enterprise/bank volume: a Postgres jobs table, a Supabase Database Webhook that triggers /api/worker, automatic retry with back-off, idempotency per invoice, and a Vercel Cron safety sweep. | Webhook acknowledges instantly; worker processes with retries | Claude | To Do |  |  | per Architecture doc
16 | 3 | Adapters & Async Pipeline | Pipeline | Verify the full clearance loop end-to-end | Verify the complete pipeline on simulation — receive invoice, classify (B2B clearance / B2C reporting), build XML, sign, submit, write back and persist — including credit and debit notes. | Cleared/reported invoices persist correctly and reconcile | Claude | In Progress |  |  | needs migration 003 applied
17 | 4 | Application Surfaces (UX) | UX | Navigable, honest onboarding journey | Rebuild onboarding as a navigable journey: clickable steps, an always-visible live connection status with one-click re-test, accurate step-by-step ERP setup guides (copy-ready webhook URL, API key and the Odoo server-action code), and no dead-ends or false 'done' states. | Any step reachable; connection manageable anytime; guides accurate | Claude | Done |  |  | fixed dead-ends found in audit
18 | 4 | Application Surfaces (UX) | UX | Business profile (seller identity) | Form to capture the legal seller identity used on every ZATCA invoice — legal name (EN/AR), VAT registration number, CRN, and the full registered address — written to the organization record. | Profile saved per tenant; gates onboarding readiness | Claude | Done
19 | 4 | Application Surfaces (UX) | UX | Invoices registry — list + detail | A consistent invoices registry on real tenant data: summary KPIs, a filterable/searchable table, and a detail view showing ZATCA status, UUID, the QR code and the signed XML. | Tenant's real invoices listed; detail view works | Claude | Done |  |  | replaced the old inconsistent page
20 | 4 | Application Surfaces (UX) | UX | Dashboard on live data | Replace the placeholder dashboard with live KPIs (cleared / reported / failed counts, SAR volume), a recent-invoices table, the persistent Demo-mode banner and the CSID-expiry warning. | Dashboard reflects the tenant's real, current data | Claude | To Do
21 | 4 | Application Surfaces (UX) | UX | Settings — connection, API keys, team | Build the three settings screens: manage the ERP connection (re-test / edit / disconnect), manage API keys (issue / revoke), and manage team members (invite colleagues) — replacing the legacy admin pages. | Settings fully functional and tenant-scoped | Claude | To Do
22 | 4 | Application Surfaces (UX) | UX | Remove legacy pages; one consistent design | Remove the leftover 'bank product', the old register page and the old admin pages so the application presents one coherent design and a single data model throughout. | No legacy/Frankenstein pages remain | Claude | To Do |  |  | consistency cleanup
23 | 5 | Notifications, Go-Live & Admin | Notifications | Email alerts (Resend) | Wire transactional email via Resend so a tenant is notified — with the invoice reference and the exact reason — whenever clearance fails or a certificate is nearing expiry. On by default. | Tenants emailed on failures and CSID expiry | Claude | To Do
24 | 5 | Notifications, Go-Live & Admin | Go-Live | Demo -> Real (production onboarding) | Build the guided go-live flow: obtain a real OTP from the Fatoora portal, re-onboard the tenant against the core (production) environment, and store the live credentials separately from the Demo ones. | A tenant can deliberately switch from Demo to Real | Claude | To Do
25 | 5 | Notifications, Go-Live & Admin | Reliability | CSID expiry tracking + warnings | Track each tenant's CSID expiry date and surface proactive warnings (dashboard + email) at 30 / 14 / 3 days so compliance never breaks silently. | Expiry warnings fire ahead of time | Claude | To Do
26 | 5 | Notifications, Go-Live & Admin | Admin | CBT internal admin console | A minimal internal console for the Convergent team: cross-tenant list, per-tenant detail (onboarding status, invoices, logs), support actions (view error, re-trigger an invoice), and a queue of 'unsupported software' requests. | Internal support tooling for the CBT team | Claude | To Do
27 | 5 | Notifications, Go-Live & Admin | Docs | Customer API docs + self-serve guides | Publish the headless-API (Mode B) reference and polished self-serve setup tutorials for Odoo, Zoho and the API so customers can onboard without assistance. | Customer-facing documentation available in-app | Claude | To Do
28 | 6 | Testing & QA | Testing | Unit tests for the compliance core | Automated unit tests for the compliance-critical code: hashing, canonicalization, ECDSA signing, TLV/QR encoding, and the BR-KSA validation rules (~25). Target high coverage on the core. | Core unit suite green (~90% coverage) | Claude | To Do
29 | 6 | Testing & QA | Testing | Integration tests | Integration tests for the Odoo/Zoho adapters, the job queue (retry + idempotency) and write-back, exercised against mocked and simulation endpoints. | Green integration suite | Claude | To Do
30 | 6 | Testing & QA | Testing | End-to-end (Playwright) tests | Automated end-to-end tests for the critical user journeys: full onboarding, an invoice clearing through the pipeline, and the failure/retry path. | Critical journeys automated and passing | Claude | To Do
31 | 6 | Testing & QA | Testing | Compliance validation gate | Re-validate clearance, reporting and credit/debit notes against the ZATCA SDK and simulation as an explicit compliance gate before deployment. | Compliance validation passes for all document types | Claude | To Do
32 | 6 | Testing & QA | Security | Security & isolation pass | Security review: RLS tenant-isolation tests, secret-handling audit, API-key authentication, and rate-limiting on public endpoints. | Security checklist cleared | Claude | To Do
33 | 6 | Testing & QA | Testing | Bug triage & stabilization | Triage and fix all defects found during testing; stabilize the build so it is release-ready. | No open blocking defects | Claude | To Do
34 | 7 | Hardening, Deploy & Launch | Deploy | Vercel production deployment | Deploy the multi-tenant application to Vercel production with all environment variables configured (Supabase keys, encryption master key, ZATCA endpoints, Resend) and the build pipeline green. | Live public URL; application boots in production | Claude + User | To Do |  |  | user provides Vercel account
35 | 7 | Hardening, Deploy & Launch | Deploy | Wire production auth + webhook URLs | Update the Google OAuth and Supabase Site/redirect URLs to the live domain so authentication works in production and the cloud Odoo/Zoho can reach the inbound webhooks (which localhost cannot). | Auth and inbound ERP webhooks work in production | Claude + User | To Do
36 | 7 | Hardening, Deploy & Launch | Deploy | Smoke tests + monitoring | Run production smoke tests and stand up logging plus basic monitoring/alerting so issues are observable. | Verified, observable production environment | Claude | To Do
37 | 7 | Hardening, Deploy & Launch | Launch | Documentation + demo walkthrough | Finalize the handoff documentation and deliver a live demo walkthrough of the complete product for stakeholders. | Handoff package + stakeholder demo | Claude | To Do
38 | 7 | Hardening, Deploy & Launch | Launch | UAT vs real ZATCA + production cutover | Run User Acceptance Testing against the real ZATCA environment with a registered device, and prepare the production cutover. Note: depends on ZATCA granting production access (external) and may extend beyond the week. | Go-live readiness sign-off | User + ZATCA | To Do |  |  | external dependency
39 | 7 | Hardening, Deploy & Launch | Launch | Go-to-market (parallel) | In parallel: publish SEO/AEO-optimized content on the Convergent (CBT) website so the free ZATCA-integration product is discoverable by search engines and AI assistants. | Product discoverable; marketing live | User | To Do |  |  | GTM track

## Status Summary
ZATCA Compliance Middleware — 7-Day Plan to Production
Convergent BT · Demo build on ZATCA simulation -> UAT -> Production
Overall
Total tasks
Done
In Progress
To Do
% Complete
Day | Theme | Tasks | Done | In Prog. | To Do
1 | Foundation & Infrastructure
2 | ZATCA Core & Onboarding
3 | Adapters & Async Pipeline
4 | Application Surfaces (UX)
5 | Notifications, Go-Live & Admin
6 | Testing & QA
7 | Hardening, Deploy & Launch
Legend
Done
In Progress
To Do